## Testing Road Map
Team 1 - Testing Scope
|  |  | Test Cycle 1 | Test Cycle 2 | Test Cycle 3
Xero Application Modules | Feature Backlog (from RCT) | StoryPoints | Execution Ends - April 25 | Execution Ends - May 02 | Execution Ends - May 09
01. Dashboard
02. User Management and Authentication
03. Settings and Configuration
04. Financial Data Entry | 4.1 Enter Financial Transactions Manually | 3 | x
| 4.2 Handle Currency Conversions | 4 |  | x
| 4.3 Save and Review Draft Entries | 2 | x
| 4.4 Edit Posted Entries | 3 | x
| 4.5 Delete Posted Entries | 2 | x |  |  | 1-2 Points → Simple CRUD operations (e.g., create/update/delete items, contacts, drafts). 3 Points → Moderate complexity (e.g., sending invoices, tracking status, viewing audit trail). 4 Points → Complex features with data processing (e.g., scheduling invoices, reports, refunds). 5 Points → High-effort tasks involving integrations, automation, or financial calculations (e.g., payment processing, managing credit limits, reconciling transactions).
| 4.6 Generate Data Entry Reports | 4 |  |  | x
| 4.7 Import Financial Data from External Sources | 5 |  |  | x
| 4.8 Create Journal Entries | 3 | x
| 4.9 Update Journal Entries | 3 |  | x
| 4.10 Delete Journal Entries | 2 |  |  | x
05. Bank Feeds and Reconciliations | 5.1 Perform Bank Reconciliation | 4 |  | x
| 5.2 Manage Bank Account | 4 |  | x
| 5.3 Manage Transactions | 4 |  | x
| 5.4 Create Rule Template | 3 |  | x
| 5.5 Manage Rules | 4 |  |  | x
| 5.6 Manage Taxes | 4 |  |  | x
| 5.7 Check Audit Trail | 3 |  | x
| 5.8 View Transaction History | 2 | x
| 5.9 Import Data | 5 |  |  | x
| 5.10 Create Chart of Accounts | 4 |  | x
| 5.11 Update Chart of Accounts | 3 |  | x
| 5.12 Delete Chart of Accounts | 2 | x
06. Invoicing | 6.1 Create Invoices | 3 | x
| 6.2 Customize Invoices | 3 | x
| 6.3. Process Payments and Integrate with Payment Systems | 5 |  |  | x
| 6.4 Manage Customers | 3 | x
| 6.5. Handle Multi-Currency Invoicing | 4 |  | x
| 6.6. Generate Bulk Invoices | 4 |  | x
| 6.7.Generate Reports and Analytics | 4 |  |  | x
| 6.8. Set Role-based Permissions for Management | 5 |  |  | x
| 6.9 Schedule Invoices | 4 |  | x
| 6.10 View Audit Trail | 3 |  | x
| 6.11 Send Automated Invoice Reminders | 4 |  | x
| 6.12 Create Items | 2 | x
| 6.13 Update Items | 2 | x
| 6.14 Delete Items | 2 | x
| 6.15 Approve Draft | 3 |  | x
| 6.16 Delete Draft | 2 | x
| 6.17 Deposit Awaiting Payment | 4 |  |  | x
| 6.18 Search (Generic) | 3 |  | x
07. Accounts Receivable | 7.1 Send Invoices to Customers | 3 | x
| 7.2 Schedule Recurring Invoices | 4 |  | x
| 7.3 Track Invoice Status | 3 | x
| 7.4 Send Payment Reminders | 3 |  | x
| 7.5 Apply Payments to Invoices | 4 |  | x
| 7.6 Process Customer Refunds | 4 |  |  | x
| 7.7 Generate Accounts Receivable Reports | 4 |  |  | x
| 7.8 Manage Customer Credit Limits | 5 |  |  | x
| 7.9 Reconcile Payments with Bank Transactions | 5 |  |  | x
| 7.10 Create Contacts | 2 | x
| 7.11 Update Contacts | 2 | x
| 7.12 Create Quotes | 3 | x
| 7.13 Update Quotes | 3 | x
08. Purchase Orders |  | VELOCITY | 50 | 68 | 60
09. Expense Claims
10. Bills to Pay
11. Accounts Payable
12. Accounting Reports